## Final Demands Tracking
Sl No | Demand No. | System Involved | SAP S4H Release | Overall Backend Status | Detailed status Descriptions | Primary Owner | Secondary Owner
1 | DMND0020213- User relationship with Sold To | WLA-SSO-C4C-CPI-APIM | N/A | Closed | Deployed into production on 01st Oct 2025 from C4C-CPI-APIM-SSO & C3 perspective all together | Samarendu | Jyothi
2 | DMND0027362- Final customer in all S4 APIs at line item level (IDEA0027080) | S4H-APIM-MDG | SAP 2025_01 Jan | Closed | Deployed into S4H production successfully. Awaiting deployment from front end. This status we keep until SFM deployment is completed. | Samarendu | NA
3 | DMND0028228- Indirect customer Identifier in SFM | C3/SFM | N/A | Closed | Deployed into production from C3. | Samarendu | SFM Front End
4 | DMND0023441 - SKF for ME- Contract Price API | Snowflake-APIM | N/A | Closed | SFM deployment is completed | Dinesh | Snowflake
5 | DMND0027327- Identifier for current price/automated price | S4H-APIM | SAP TBD | ON HOLD | Pre-Study Approved.On Hold due to project west. | Dinesh | NA
6 | Indirect Partner - SPQ+ (Demand no is missing) | SPQ+- APIM | N/A | ON HOLD | 1)Business discussion is with Mickey Ekroth is in progress. 2)This demand should be driven from SPQ+ technical team from pre study and realization point of view. 3)Overview documentation could be facilitated by us | SPQ+ Team | Samarendu
7 | DMND0028814- Lead Time for N2 items in SFM | S4H-MDG-Snowflake-APIM | SAP 2025_10 Oct | Closed | Deployed into production successfully with cut over activities completed. | Samarendu | NA
8 | DMND0028407- PnA Response Vs. Order Simulation | S4H-APIM | SAP 2025_03 Mar | Closed | Deployed into production from S4H, APIM & SFM successfully. No isue is noticed yet. | Samarendu | NA
9 | DMND0028917 - Display/Download Advanced Shipping Notice (ASN) & Packing slip | S4H-APIM | SAP 2025_11 Nov | Incident Fix | We need to fix a global issue of error in ZSH1 ouput type because of missing customer email ID with note ASN. We have incident INC2687825. ABAP team has parked the changes due to: 1) objectet is locked under Project West changes 2) There is hard freeze until june/july. | Dinesh | NA
10 | DMND0028406- Error messages of PnA | S4H-APIM | SAP 2025_03 Mar | Closed | Deployed into production from S4H, APIM & SFM successfully. No isue is noticed yet. | Dinesh | NA
11 | DMND0029205- Order book robustness/Ecommerce Suit Project | S4H-APIM | N/A | ON HOLD | Pre-Study Approved.Awaiting SKF leadership to provide formal approval to start Ecom suite POC on SAP Commerce Cloud platform. Indrajit & Christian W to guide us further for next steps | Samarendu | NA
12 | DMND0029521- C4C Ticket Enhancements | C4C-APIM | N/A | DAB Rejected | PS Approved, awaiting confirmation from DAB to commence realization. | Samarendu/Satish | Satish
13 | DMND0029860- Scheduling Agreement Orderbook | S4H-APIM | SAP 2025_09 Sept | Closed | Deployed into production, although front end changes is not yet started. | Dinesh | NA
14 | DMND0029812- Buffer SO in SFM from APIM | APIM | N/A | Closed | Action items with APIM & SFM frontbend to increase the time out duration based on recent discussions & recent production cases. | Samarendu- As secondary support Sukanya- Primary support | NA
15 | Digital certificate - DMND0024256 (New) | S4H-APIM-DocuSign-Open Text | SAP 2026_03 Mar | DAB Rejected | PS Approved, awaiting confirmation from DAB to commence realization. | Samarendu | Dinesh
16 | DMND0030127 - Get Product Carbon Footprint data into digital services for external customers | PIM-SFM | N/A | Closed | Pre-Study has been approved across all stakeholders. SFM needs to start building. Demand has been closed in Service now, as no back end development is needed | Samarendu | PIM
17 | DMND0030128- Product Material Compliance data in digital services | Snowflake-APIM-SFM | N/A | Closed | Deployed into production from APIM. SFM sprint to consume this service is yet to happen. | Samarendu | NA
18 | DMND0029897- SKF For Me Overall Performance/Overall demands and issues in SFM pain points consolidation | Integration | N/A | Closed | Pre study was approved by Indrajit. This Pre study is with nothing to enhance or implement further rather consolidating all the hiccups SFM has and the resolutions which are across other multiple demands we are already working upon. | Samarendu | NA
19 | DMND0029323 Create C4C ticket enhancement | SFM | N/A | Closed | This will be driven in SFM front end adjusting field properties | Front End/Samarendu | Satosh
20 | DMND0031243- List of Credit Note data & download PDF | SFM-S4H-APIM | N/A | Closed | Pre-Study Approved.No SAP S4H development, master data set up is required in testing & prod once SFM changes is in place | Dinesh | NA
21 | DMND0031268- SFM Project west carve out | SFM-S4H-C3-Others | SAP 2025_10 Oct | Closed | Wave 1 deployment is done for Spain successfully. | Samarendu | Darshit
22 | DMND0031349- MVP - Service Persona | Service Max | N/A | DAB Rejected | PS Approved, awaiting confirmation from DAB to commence realization. | Samarendu | Service Max
23 | DMND0031879- Error Monitoring & Analysis | S4H | SAP 2025_11 Nov | Closed | Deployed into production this week. Cut over completed | Samarendu | NA
24 | DMND0031834- Relationships Location/ Sublocation/ Asset/ Bearing arrangement – to get status update on condition monitoring recommendation | Service Max- SFM | N/A | DAB Rejected | PS Approved, awaiting confirmation from DAB to commence realization. | Dinesh | Service Max
25 | DMND0031833- Indirect customer ship to address | S4H-APIM | TBD | ON HOLD | On Hold due to project west. | Dinesh | NA
26 | DMND0031832- Status update of Remanufacturing request/Field Service WO | Service Max- SFM-APIM-S4H-SPQ+-C4C | TBD | Pre-Study Phase | Business alignment is required and it's on hold for time being as other priotized idemands are picked up | Dinesh | Service Max
27 | DMND0031806-Indirect customer should be returned by order fetch API | S4H-APIM | SAP 2025_11 Nov | Closed | Live in production since 23-Nov | Dinesh | NA
28 | DMND0031803- Master Persona in SFM/C4C | C4C-APIM | N/A | Closed | SFM sprint has been kicked off and its under development | Samarendu | Jyothi
29 | DMND0031826- QMPS availability (SAP supplier) to PnA API/ Full Availability API | S4H-APIM | SAP-2025-11 Nov | Closed | Deployed into production this week. Cut over completed | Samarendu | NA
30 | DMND0032383- Display individual Product Carbon Footprint values in SFM | Snowflake-APIM | N/A | DAB Rejected | PS Approved, awaiting confirmation from DAB to commence realization. | Samarendu | Snowflake
31 | DMND0032694- Version 2 Lead time dataset in Snowflake will be based on automated calculations from data in QMPS/ MPSS/ OMPS | Snowflake-APIM | N/A | Screening Phase | Further business alignment with Snow flake is in progress. | Samarendu | Snowflake
32 | DMND0032689- PFAS certificate | Snowflake-APIM | TBD | ON HOLD | POC is successful & confirms all relevant data is available in Snwoflake existing compliance view. These demands would be picked up in 2026 once parent certificate demand is delivered & deployed. | Samarendu | Snowflake
33 | DMND0032687- TSCA section 6(h): US law | Snowflake-APIM | TBD | ON HOLD |  | Dinesh | Snowflake
34 | DMND0032686- Canada CEPA 1999: Canadian law | Snowflake-APIM | TBD | ON HOLD |  | Dinesh | Snowflake
35 | DMND0032685- California Proposition 65: Californian law | Snowflake-APIM | TBD | ON HOLD |  | Dinesh | Snowflake
36 | DMND0032684- Persistent Organic Pollutants | Snowflake-APIM | TBD | ON HOLD |  | Dinesh | Snowflake
37 | DMND0032844 - Modify discontinued item warning | S4H-PI-WCL | SAP-2026-04 Apr | DAB Rejected | PS Approved, awaiting confirmation from DAB to commence realization. | Samarendu | NA
38 | DMND0032797 (Lead time service version 3) - “SPQ+ / ZCATP to consume the lead time API” | S4H-SPQ+ | SAP-2026-06 May | Partally Deployed | S4H deployment is in place, SPQ+ realization is about to start | Samarendu | SPQ+
39 | DMND0032864- Status-update on C4C Ticket | C4C-APIM-SFM | N/A | DAB Rejected | PS Approved, awaiting confirmation from DAB to commence realization. | Samarendu | Satish
40 | DMND0033050- Onboarding internal customer on SFM | S4H-APIM | TBD | ON HOLD | Business alignment with Johanna Lindblom is pending. Although technical POC was successful | Samarendu | NA
41 | DMND0031830- Export Consolidation fields in Order fetch | S4H-GTS-APIM | SAP-2025-12 Dec | Closed | Moved to production on 22-Dec | Dinesh | NA
42 | DMND0032391- C4C Ticket on Certificate PMC data missing for Reach & RoHS | C4C-APIM | N/A | DAB Rejected | PS Approved, awaiting confirmation from DAB to commence realization. | Samarendu
43 | DMND0032822- Add service materials in the service catalogue in SFM | MDG-S4H-WCL-PIM-SFM | TBD | Under Realization | Realization would be part of CMS solution 1st version, not exactly w.r.t. option 1-3 right now. Later phase, it would be catered into long term solution with option 2. | Samarendu | SFM Front End
44 | DMND0033700 - Solution for service delivery related communication with the customer | SVMX-APIM | N/A | DAB Rejected | PS Approved, awaiting confirmation from DAB to commence realization. | Dinesh | Service Max
45 | DMND0034136- Activate currency conversion in PnA | S4H-APIM | TBD | DAB Rejected | PS Approved, awaiting confirmation from DAB to commence realization. | Samarendu | SPQ+
46 | DMND0031674- Goods Marking in SFM Quote to SPQ to SAP Sales Order Flow | S4H-SPQ+-SFM | TBD | DAB Rejected | PS Approved, awaiting confirmation from DAB to commence realization. | Samarendu | SPQ+
47 | DMND0034282: Display OMR error, refund, cancellation message against SAP delivered products in SFM | S4H-APIM | TBD | DAB Rejected | PS Approved, awaiting confirmation from DAB to commence realization. | Dinesh | NA
48 | DMND0033799- Consume Export Control Classification Number (ECCN) from GTS to S4H Order Fetch API | GTS-S4H-APIM | TBD | DAB Rejected | PS Approved, awaiting confirmation from DAB to commence realization. | Dinesh | GTS
49 | DMND0033732- Create field service WO | SVMX-APIM | TBD | DAB Rejected | PS Approved, awaiting confirmation from DAB to commence realization. | Samarendu | Service Max
50 | DMND0033528- Consume PnA & Lead Time in Quote flow Price & Availability check in quote request - Special price business scenario | SFM-APIM-SPQ | SFM_2026_07 July | Under SFM Realization | SFM meetings concluded on 24th Feb, they have plan to start this demand realization from April onwards Special price scenario- needs to adopt now (Included in August 2026) | Samarendu | SFM Front End
51 | DMND0034755- CMIR Handling in SFM | WCL Backend-Findwise | WCL/FW_2026_08 Aug SAP_2026_09 Sept | Pre-Study Phase | This pre-study has been hold due to PW from WCL, it will be taken up after May'2026 | Samarendu | SFM Front End
52 | DMND0034407- C4C Contacts sync | C4C-SFM | APIM/SFM_2026_05 May | Deployed into PRD | Deployed in APIM production | Samarendu | Jyothi
53 | DMND0034238 - Add several attachments when creating a ticket in C4C | C4C-APIM | TBD | DAB Rejected | PS Approved, awaiting confirmation from DAB to commence realization. | Dinesh | Satish
54 | DMND0035486- Dangerous goods display over SFM portal | GTS-MDG-SFM | TBD | DAB Rejected | PS Approved, awaiting confirmation from DAB to commence realization. | Samarendu | PIM/FW
55 | DMND0031831- Reman WO create and fetch | SVMX-SFM | TBD | DAB Rejected | PS Approved, awaiting confirmation from DAB to commence realization. | Samarendu | Service Max
56 | DMND0035721-Display correct item status in order book | S4H | TBD | Pre-Study Phase | PS is in progress | Samarendu | NA
57 | DMND0033794 - Display down payment orders & advance payment delivery block | S4H-SFM | TBD | Under SFM Realization | Pre-study has been approved by Indrajit and SFM development is in progress. | Dinesh | SFM Front End
58 | DMND0032634 - Display CMIR in contract price service | Snowflake-SFM | NA | Closed | It has been deployed in production and Audrey confired to close it. It has been closed. | Dinesh | Snowflake
59 | DMND0035777 - Display product group & discount in Price & Availability check. Establish new architecture to display List Price tag. | Snowflake-APIM-SFM | APIM/SFM_2026_08 Aug | Under Realization | The pre-study has been approved by Indrajit and the same has been forwarded to APIM team to start the development. As per APIM update, development will be started after 10-Aug. | Dinesh | Snowflake
60 | DMND0036521 - Display freight & packaging surcharge | Snowflake-APIM-SFM | NA | Pre-Study Phase | Pre-study is in progress, we have a meeting scheduled with business in next week. | Dinesh | Snowflake
61 | DMND0036801 - SFM Invoice Download Improvements | S4-APIM-SFM | TBD | Pre-Study Phase | Cecilia explained the requirement on 29-Jul, we have started the pre-study. | Dinesh | SFM Front End
62 | DMND0037018 - SFM - Schedule Agreement OB Improvement | SFM | NA | PS Yet to start | Kick off discussion happened.We have not started the pre-study. | Dinesh | NA
63 | DMND0032862 - SKF can edit a quote when in status sent to customer. | SPQ+- APIM | NA | Screening Phase
64 | DMND0028879 - SPQ+ backend performance improvements | SPQ+- APIM | SPQ+_2026 04 April | Closed | Completed in SPQ | Mickey | NA
65 | DMND0027119 - Soprex Inquiry and Quote Q2 2024 | SPQ+- APIM | NA | Closed | Deployed in SPQ | Mickey | Radomir
66 | DMND0025522 - External tracking ID and link to external forwarder | EM | NA | Closed | Deployed in SAP EM | Andreas Stoller | NA
67 | DMND0029011 - LSB Co2e saving certificate | Service Max | NA | Closed | Deployed in SVMX | Andrew Dollinger
68 | DMND0030241 - Add service lines in the Inquiry/ Quote process | SPQ+- APIM | NA | Screening Phase
69 | DMND0030242 - Partial quantity ordering from quote | SPQ+- APIM | SPQ+_2025 11 Nov | Closed | Completed in SPQ | Mickey | Radomir
70 | DMND0035401- Prevent duplicate quote/ display quote price in quote request | SFM-APIM | NA | Price & Availability check in quote request - Special price business scenario | POC is successful, yet to have kick off for PS | Samarendu
71 | Display unit price for commercial discount in Price & Availability check (JIRA Ticket/No Demand No) | SFM | SFM_2026_08 Aug | Under SFM Realization | POC was successful and explained the requirments to adopt in SFM front end | Samarendu | SFM Front End
72 | DMND0036275- SKF for Me - Selectable Bill-To at Order Entry (similar to Ship-To selection) | SFM | SFM_2026_06 June | Closed | Completed in SFM | Samarendu | SFM Front End

## Draft DemandsIDEAs Tracking
Action required by EMEA E-Business - Work Group
Roadmap | Demand no | Title | Persona | Triage quarter | Application Expert | Business Analyst | Action/ Responsible | Business requirement in scope | Rating (business), | Rating date | Invalid/ reject | SAP template/ NEXUS | ON HOLD
Q2/26 -Q127 | [8 empty] | scale 0 to 10
N | DMND0036284 | Display the number of pieces the customer is allowed to buy | Buyer |  |  |  | Handover this demand to Nexus project when the timing is right. | The available quantity the customer can see, (prompt, secondary & full availability) has been adjusted so that the customer can only see as many pieces as she is allowed to buy without eating from the availability of another customer. |  |  |  | Y
The business logic for display of availability is dynamically adjusting the available quantity based on the actual demand & supply situation at the time. The customer’s outstanding order book +/- 5 days from current date is considered.
The IT architecture for large order filter is optimized, robust & scalable. The business logic resides in the relevant business system which will in real time send updated availability numbers to all relevant satellite systems: SAP, demand chain planning, warehouse systems, e-commerce portals etc.
N | DMND0036302 | Prevent the customer from seeing availability & lead time for obsolete items | Buyer |  |  |  | Handover this demand to Nexus project when the timing is right. | S4H must for all materials (on pack variant level) send distribution chain material status & cross plant material status to WCL database in the Product sync integration, for the material statuses 50 (released), 85 (to be discontinued). In a scenario when a material has a replacement material S4H must similarly send the relationship between the material & its replacement material & the material status & the cross plant material status for the replacement material. |  |  |  | Y
The supply system for legacy supplied & SAP supplied items (both) must send availability & lead time to S4H. S4H must distribute availability & lead time to consumer system for example SFM. In scenario when the requested quantity is available for a material with material status 85 SAP will automatically place order for that material (SKF wants to deplete the stock). In a sceanario when the requested quantity is not available for the item with status 85 the SAP will place the order with replacement item.
N | DMND0036303 | Display dangerous goods across SAP template | Buyer |  |  |  | Handover this demand to Nexus project when the timing is right. | See Servicenow |  |  |  | Y
N | DMND0031156 | Listing/Exclusion list for material | Buyer | Q2, 2026 |  | Hanna | (1) Handover this demand to Nexus when the timing is right. | The business requirements are to get a more sophisticated way to manage exclusions from the assortment in S4H template. The expected business benefit is less manual maintanance/ more time to focus on developing new business. In as-is solution exclusions are managed on sales unit level. The requirement on the to-be solution is to add exclusion management on the following levels: sold-to, customer group, supply product line (SPDIV), delivery district, SPC, combination sales org/ matrix group. This demand will impact S4H: VB01/02/03 Listing/Exclusion & ZCATP, SPQ+ PnA, & SFM PnA & Create Sales Order. | Eurotrade 9 | 2026-01-04 |  | Y
[7 empty] | (2) If we are to do any more work on this the next steps are as follows: |  | Iberic 8 or 9, Turkey 8 or 9, Nordic 6 or 7
[8 empty] | Please note: SFM to consume the exclusion list from S4H system is excluded from the scope of this demand & to be developed in separate demand: DMND0036152. | Germany 10
Samarendu/ Dinesh check the as-is configuration possibilities in S4H
BA to (1) align the business requirements & scope of this demand with IT Samarendu/ Dinesh & Florian May
Patrik Andersson investigate/ get back if there are additional product related levels that are relevant to consider to include in the scope for this demand.
N | DMND0035455 | Converting offer to order to different Sold to account | Buyer |  |  | Cecilia | Cecilia Ekman to follow-up with Johanna Bjorneras / confirm the outcome of the testing to use different ship-to per demand type & TMC. If testing is successful this demand is to be rejected. | With this demand the customer can in quote convert stage change ship-to before sending in the order. The ship-to will in customer master be pointed to a specific supplying warehouse. The effect is that the SRAL routing will follow the warehouse linked to ship-to. When converting the quote to order the customer will when they select ship-to decide from where the goods will be supplied. | Middle East (EU02) 10 | 2026-04-03 | Y
Y | DMND0034500 | Display correct item price in order book | Buyer | Q2, 2026 |  | Hanna | Ok to start as soon as Samarendu/ Dinesh has time. Samarendu/ Dinesh will search for the POC which was done earlier this year and confirm when we can move this to screening. | Currently the item price in SFM order book is not same one as sent in the order acknowledgement from S4H. Instead the item price in SFM order book contains any header surcharges & discounts (both). With this demand the item price in SFM order book is same one as sent in the order acknowledgement from S4H. The scope of this demand is to change the S4H Order Fetch API response message, to align with the order acknowledgement from S4H. | 6 | 1/21/2026
N | DMND0036801 | SFM invoice download improvements | Buyer | Q3, 2026 |  | Cecilia | Is on the agenda to be rated by the Digital CX Experts August 19th. | Turkey: currently we have disabled the download button for Turkey. There are legal requirements to not send invoices directly to the customer and therefore a different process was defined. We would need to have an investigation if we are able to support invoice download in SFM for Turkey. Business responsible: Asli Sezgin
Czech Republic: there is a legal requirement to have the invoice as a signed pdf invoice. In SAP there is a process that the standard pdf invoice is also converted to a signed version and this is then send to the customer. Unfortunately SFM download for invoices provides the standard version. Business responsible: Petra Buryszova
Eurotrade EU01: In SAP for customers the domestic and export invoice is set up. Both are send to TRIM, but only the export invoice is send to the customer. Unfortunately in SFM the "latest" invoice which is saved in TRIM is downloadable and therefore sometimes the domestic invoice is provided to the customer which causes manual interaction from CX. Business responsible: Petra Buryszova / Josipa Bakovic
N | DMND0037018 | SFM - Schedule Agreement OB - Improvement of data quality display - by removing lines delivered and invoiced | Buyer | Q4, 2026 |  | Cecilia | Cecilia Ekman Aligned requirements with Audrey. Is on the agenda to be rated by the Digital CX Experts August 19th. The SFM filtering logic to be outlined & documented in PS by this demand. | SFM front-end demand to filter. |  |  | Y
Y | DMND0033528 | Price & Availability check in quote request - Special price business scenario | Buyer |  |  | Hanna | Hanna Sandberg to ask the Digital CX Experts to rate this demand August 5th. Depending on the outcome this demand to be aligned with Mickey Ekroth & Samarendu Kumar. | SFM has recently developed an enhancement to the quote request functionality which ensures that SFM will before allowing the customer to request a quote check if there is already a price prepared for the combination of Sold-to/ Indirect customer, product & pack size in master data.
The business requirement that still remains to be done as part of the scope of this demand is to in special price scenario if the Sales unit is Germany send the special price request to S4 HANA system and for all other Sales units in Europe, Africa & Middle East send the special price request as a quote request to SPQ+. A C3 setting is required to on Sales unit level control to which backend system the special price request is to be sent.
Y | DMND0035401 | Prevent duplicate quote/ display quote price in quote request | Buyer | Q3, 2026 |  | Hanna | Hanna Sandberg to call for meeting with Samarendu & Mickey Ekroth to align this requirement. The guidance from Samarendu is PnA check is not technically feasibly option for performance reasons. Instead align feasibility for direct call to SPQ+ with Mickey Ekroth. | The scope of the first version is to in SFM request quote do a call to SPQ+ to identify if there is already an existing quote (under negotiation or accepted) for the same Sold-to/ Indirect Partner/ item/ quantity. If yes then don't allow customer to request new quote but instead allow the customer to continue the negotiation or place sales order depending on if the quote is under negotiation or accepted from before. | 8 | 2026-04-03
N | DMND0036781 | SKF FOR ME _ the ability to select the currency when adding a recommended price in inquiry process | Buyer | Q3, 2026 |  | Hanna | Hanna Sandberg to ask the Digital CX Experts to rate this demand August 5th. Depending on the outcome this demand to be aligned with Mickey Ekroth & Samarendu Kumar. | With this demand the customer will in quote request have the ability to in special price scenario press a button that allows them to convert the currency of the price displayed in SFM from order currency to quote currency. This will make it more efficient for the customer when sending request for special price business.
N | DMND0036803 | SKF For Me - enable to consume SPQ+ identifier "allow change delivery address" for quote to order process | Buyer | Q3, 2026 |  | Cecilia | Is on the agenda to be rated by the Digital CX Experts August 19th.
Y | DMND0029348 | New pricing condition for current price | Buyer | Q3, 2026 |  | Hanna | Hanna sent an email 2026-07-27 to Johanna Bjorneras for her to confirm if this PS can be initiated. |  | 10 | 2025-10-12
Y | DMND0034873 | Customer can edit a quote when in status sent to SKF | Buyer | Q4, 2026 |  | Cecilia | Cecilia Ekman to confirm, after Project West is completed & after DMND0032862 - Possibility in SPQ+ for SKF people to edit quotations when in status "sent to customer" is deployed in backend (SPQ+ & APIM) production, when SPQ+/ Soprex are available to work on this demand. | If a quote have status sent in SFM it should still be possible for the customer to send in modifications even if SKF have not sent a new version of the quote. In SPQ+ the SKF user need to be able to see if the customer has sent in modification(s) to the quote that include new information to consider when managing the quote. It should be possible even if the quote have been sent for approval & also when a country is using quote automation. | 10 | 1/21/2026
N | DMND0030946 | Less conditions to provide COM on PnA response in WCL/SFM | Buyer |  |  |  | This demand is in stage Screening run by Edson J Lagos Global COH triage team. We keep it in this list of draft demands for now. Hanna Sandberg to follow-up with Edson in Nov 2026 to see if we can remove this demand from our list. |  |  |  |  | Y
N | DMND0035871 | Maintain master data/ suppliers with unacceptable COM for Sold-to | Buyer | Q2, 2026 |  | Hanna | Handover this demand to Nexus project when the timing is right. | The business requirements are to in SAP Customer master for a Sold-to maintain a list of country of manufacturing (COM) which are nonacceptable. Also it could be maintained in similar way as POC/ BRF table. When the customer User checks price & availability in SFM an indicative COM would be displayed accordingly (no nonacceptable COM will be displayed). This way when the order is placed & eventually when the order line is allocated consistently the same logic to avoid the nonacceptable COM would be used for SAP supplied items & legacy supplied items (both), hence the logic would impact S4H SRAL determination. This demand would enable SFM to display indicative COM in PnA and confirmed COM in the order book. The COM may not be same in PnA & when the order line has been allocated, but SKF can guarantee that an item will never be supplied by a nonacceptable COM. | Middle East (EU02) 10 | 2026-01-04 |  | Y
[7 empty] | Dependency on DMND0030946. We first need to see if that demand will solve the business requirement to display indicative COM. If yes then maybe DMND0035871 is no longer valid. |  | Iberic 6 or 7, Turkey 5 or 6, Nordic 3 or 4
Germany 4
If we are to do any more work on this the next steps are as follows:
Samarendu/ Dinesh to prepare POC/ align with Abhishek/ Anirban etc. Please also check these:
INC2708534 -> DOH INC2720424
Y | DMND0031835 | Request/ display technical ticket | Buyer | Q3, 2026 |  | Cecilia | Markus Hoehn has stopped this for now. On hold. Focus is on the chatbot. | Send the relevant fields & the relevant identifiers from SFM to C4C, to route this ticket to the relevant team or role/ based on the SKF organizational hiearchy. |  |  | Y
Hanna Sandberg to add to agenda/ follow-up in Pulse or Triage meeting after summer.
Cecilia Ekman to align with CX expert network/ get their rating on a scale from 0-10. Develop UX designs & handover to Markus Hoehn. Reject this demand in Servicenow. Add it to the sheet "SFM front-end demands" for tracability purposes/ to remember what we did.
Y | DMND0027327 | Consume the new pricing condition from DMND002348 | Buyer | Q4, 2026 |  |  | No action. Dependency on DMND0029348 |  | 10 | 2025-10-12
Y | DMND0035625 | Display country & city of supplying warehouse in quote list | Buyer | Q4, 2026 |  | Hanna | Hanna Sandberg is responsible to reject this demand six months after DMND0031830 Order Book overhaul demand has been deployed in SFM production (planned to be deployed mid/ end April 2026), when we know for sure that that demand is enough to cover the business requirement to display WH/ COM in order book. When it comes to display of suplying WH in quote this exists today in quote PDF/ hence customer can see it there. |  | 8 | 2/18/2026 | Y
If we are to drive this demand then the next step is to align it with Samarendu & Mickey Ekroth as it requires changes in the API from SPQ+ to SFM. The rating of this demand from all other sales units than EU02, EU01 & FR01 is 5, as they will not use this capability as it is a specific requirement to support export business.
Y | DMND0031827 | Display status update when an item has been replaced | Buyer | Q1, 2027 |  |  | Handover this demand to Nexus project when the timing is right. | SFM dashboard updated 6 months prior to an item will become replaced/ obsolete | 10 | 1/15/2025 |  | Y
Y | DMND0032694 | Optimized lead time solution with automated logic | Buyer | Q1, 2027 |  | Tilman | From a technical perspective, @Samarendu Kumar and @Dinesh Kumar have recently given green light to start DMND0032694, Optimized lead time solution with automated logic, when the required resources to work on this IT pre-study have been formally assigned to it, by @Monali Roy. We know that the required resources are Mats B Petersson, Herman Ruul, QMPS (e.g., development done already by Herman but the lead time data need to be moved from DWH_0004 into DWH_0067 ), and one Snowflake developer that can bring the lead time data from MPSS and OMPS into one Snowflake dataset e.g., DWH_0067 . | SFM, SAP ZCATP & SPQ+ gets lead times for all Product Lines from Snowflake. The lead time dataset in Snowflake is manually updated by the Supply Chain Planners. | 9 | 1/15/2025 |  | Y
The lead times are automatically sent from the supply chain planning systems (currently OMPS, MPSS & QMPS) to the Snowflake lead time dataset (or other master source if relevant). SFM, SAP ZCAPT & SPQ+ will consume the lead times from the source.
Monali Roy must complete the effort estimation & resource plan, & confirm that the technical application expert from Snowflake /OMPS /MPSSS are available. After that confimed/ ok by the technical team to move from Draft to Screening.
Y | DMND0032384 | Most environmentally friendly transport option | Buyer | Q1, 2027
Y | DMND0031836 | Display delivery alternatives with most environmentally friendly transport option | Buyer | Q1, 2027 |  |  |  | The customer will select between four generic delivery options; Standard delivery, Alternative delivery, Land express & Air express. |  |  |  | Y
Behind each delivery alternative SKF would combine the Delivery priority, Transport mode & demand type for each customer classification from the slowest combination to the fastest combination. The most environmentally friendly transport alternative is highlighted.
Every time the customer places an order she can select how much she is prepared to pay for the reduced total time between the date when the order is placed & the delivery date.
N | DMND0031673 | Register/ list list pallet returns | Buyer |  |  | Cecilia | 2026-04-29: Pause this demand for now. There is one demand driven by Industrial E&A Logistics with the scope to standardize the pallet return process across Industrial E&A. It is now stopped by DAB. We will get back to this after Project West once the IT landscape freeze due to Automotive split is released. | The customer can register a pallet return in SFM & get the return material authorization from SFM and a unique reference number. The customer can see a list of all their ongoing pallet returns in SFM.The customer can filter the list of pallet returns using the unique reference number, status, date range, creation date etc. |  |  |  |  | Y
[7 empty] | When we are to pick up any work on this demand the next step is as follows: | With this demand Industrial region E&A would get one standardized process for pallet returns on high level including following: customer registers pallet return in SFM & immediately receives the return label from SFM. The receiving warehouse has been determined automatically based on sales unit, sold-to, sales order number, pallet type etc., instantly by the solution before making the return label available in SFM. Currently there are multiple manual steps in the pallet return handling process including also crediting the customer for pallet returns. The IT pre-study to explore which steps to automate in the first version/ progress before perfection. HOMEWORK for everyone: Please reflect on the pallet return process for your Sales unit. Manual work is high cost to serve, compared to having a digital service that step by step can be evolved to optimize/ automate this work. What we want to do here is to relieve time for CX people to focus on developing the business with the customer instead of handling manual administration related to pallet returns. Is this something you want us to explore / digitalize or not?
Cecilia Ekman to align with CX expert network the busines value of adding pallet return service in SFM & get their rating on a scale from 0-10.
N | DMND0036152 | SFM to consume the listing/ exclusions from assortment | Buyer |  |  | Hanna | Dependency on DMND0031156 Listing/ exclusion for material on Sold-to level. No further action until the required capability has been developed in the S4H template. | When SFM calls Findwise API (already in place) SFM will also make a call to check listing/ exclusions maintained by business in S4H template & dangerous goods. The business requirement is to enable SFM to know the listing/ exclusions maintained by business in S4H system. | Eurotrade 9 | 2026-01-04 |  |  | Y
Iberic 8 or 9, Turkey 8 or 9, Nordic 6 or 7
[8 empty] | Dependency on S4H template demand: DMND0031156 Listing/ exclusion for material on Sold-to level | Germany 10
N | DMND0033050 | Onboard internal customer | Buyer |  |  |  | Michael Jaeger to get back and confirm that the users in SKF Lubrication systems and other internal customers have given their commitment to use SFM. | CS Germany wants to onboard SKF Lubrication Systems to use SFM for order entry and PnA check. | 8 | 1/21/2026
N | DMND0031833 | Relationship Indirect Partner/ Ship-to delivery address | Buyer |  |  | Hanna | Hanna Sandberg to align with Service expert network/ get their rating on a scale from 0-10.
N | DMND0035779 | SFM to allow final customer on line level for the flow from request quote to convert quote to order | Buyer |  |  |  |  | Today it is possible for the Distributor to in SFM place a sales order with different final customer on different lines in the same order. Today it is not possible for the Distributor customer to do the same when they request a quote. For quote final customer is a header field only. | 1 | 2026-04-03
N | DMND0034758 | Make the lead time API into a Post call, (to handle multiple items in the same request) | Buyer
N | DMND0034124 | Consume credit note status from the billing document API | Buyer
N | DMND0035426 | Statement on Export Control certificate in SFM | Buyer |  |  |  | Dependency on DMND0024256, Certificate REACH/ RoHS | See email sent by Hanna to Tobias Ott 2026-01-30 |  |  |  |  | Y
N | DMND0032684 | Persistent Organic Pollutants certificate in SFM | Buyer |  |  |  | Dependency on DMND0024256, Certificate REACH/ RoHS | [5 empty] | Y
N | DMND0032685 | California Proposition 65: Californian law | Buyer |  |  |  | Dependency on DMND0024256, Certificate REACH/ RoHS | [5 empty] | Y
N | DMND0032686 | Canada CEPA 1999: Canadian law | Buyer |  |  |  | Dependency on DMND0024256, Certificate REACH/ RoHS | [5 empty] | Y
N | DMND0032687 | TSCA section 6(h): US law | Buyer |  |  |  | Dependency on DMND0024256, Certificate REACH/ RoHS | [5 empty] | Y
N | DMND0032689 | PFAS certificate | Buyer |  |  |  | Dependency on DMND0024256, Certificate REACH/ RoHS | [5 empty] | Y
|  | Long term declaration | Buyer |  |  |  | Dependency on DMND0024256, Certificate REACH/ RoHS | [5 empty] | Y
N |  | Remanufacturing CO2e certificate | Buyer |  |  |  | Dependency on DMND0024256, Certificate REACH/ RoHS | [5 empty] | Y
N |  | Maintain CMIR (customer own designation) on Final variant (ZVER) level instead of on pack variant level (ZHAL) | Buyer | [8 empty] | Y
|  | Display unit price for commercial discount in Price & Availability check | Buyer |  |  |  | Samarendu Kumar/ Dinesh Kumar has executed POC June 2026 & given the guidance for this demand to be delivered as short-term fix by SFM. This line is to create a backend SAP template demand instead of solving it in SFM. | S/4 HANA would have to change the field structure, calculate on runtime & send the values for each scale. |  |  |  | Y
N | DMND0029205 | Filter the SFM order book on Ship-to, Indirect Partner, Invoice no, LOT no, Package no | Buyer |  |  |  | No action. Dependency on NEXUS/ SKF investing in IBM e-commerce platform |  | 10 | 2025-10-12 |  | Y
N | DMND0036479 | Filter the SFM order book on item status Awaiting payment | Buyer |  |  |  | No action. Dependency on NEXUS/ SKF investing in IBM e-commerce platform |  |  |  |  | Y
N |  | Filter the SFM order book on item status Incomplete | Buyer
N | DMND0031839 | Replace product sync interface in WCL backend with new architecture | Buyer |  |  |  | No action. Dependency on NEXUS/ SKF investing in IBM e-commerce platform | Master the relationship Sold-to/ Product elsewhere. Change to regional/ EMEA assortment mgmt |  |  |  | Y
N | DMND0031837 | New architecture building block for e-commerce configuration settings | Buyer |  |  |  | No action. Dependency on NEXUS/ SKF investing in IBM e-commerce platform | Replace WLA as master for the e-com configuration settings on Sales unit/ Sold-to/ User level |  |  |  | Y
N | DMND0031838 | Sales Unit/ Sold-to input parameters/ item/ SAP Billing API | Buyer |  |  |  | No action. Dependency on NEXUS/ SKF investing in IBM e-commerce platform | Filter on invoice nbr/ Sales order number etc. Limitations due to pagination |  |  |  | Y
N | DMND0033793 | Additional Filter shown in Order Book in SFM | Buyer |  |  |  | No action. Dependency on NEXUS/ SKF investing in IBM e-commerce platform | Filter by requested date/ invoice date. Save last filter button. Sort by requested date from oldest to newest & by delivery date |  |  |  | Y
N | DMND0036574 | Display intuitive packaging options/ standardized across warehouses | Buyer
N |  | Depending on customer classification (A, B or C) the customer can edit/ cancel the order differently. | Buyer |  |  |  |  | The firs version of this business requirement was developed under the scope of DMND0036475 The customer can from item level order book send request (ticket) for CX to manually edit/ cancel
The new business logic will be explored, and the following aspects will be part of the consideration, before proposing a new logic: Customer Category, Customer Account Type, Order Line status, business climate (relation between supply and demand considering the relevant market/ industry), PC code, PS value, OMR code and any other material related codes that are relevant.
In general; the earlier the order line is in its life cycle the more likely it is that a modification and/ or cancellation is possible. The flexibility to edit/ cancel an order line will be higher for make to stock items, compared to for make to order items. The business climate will also be continuously considered/ weighted into the algorithm over time, to protect SKF from any unwanted exposure to unpredictable business risk.
N | IDEA0034311 | Preferential Origin in SKF For Me | Buyer |  |  |  | This business requirement (idea/ demand) belongs to Sub-portfolio SAP Sales & Distribution - E&A. Also it might happen that this one is solved via INC flow instead, Hilde Peters decides that. | Set-up the relevant BRF table to accommodate for CHE0220 (CH01): Preferential Origin |  |  |  |  | Y
N |  | Relationship User/ Indirect Partner | Buyer |  |  |  | Dependency on strategy decision shall users that represent indirect partners be allowed to log in to SFM? They are not contracted customers. | [5 empty] | Y
N |  | Implement Service model for Customer category A, B and C | Buyer |  |  |  | The required business maturity is not in place. Dependency on strategy decision as this would require transformation of the way of working/ focus on change management. | Purpose to replace WLA with defaulted e-com settings depending on customer category |  |  |  |  | Y
N |  | Defense customers can request 2.1 from SFM | Buyer |  |  |  |  | Place sales order, See order book, See invoices, Check PnA, Check Product Catalogue. (Compliance, Cyber Security, Legal, GDPR requirements) |  |  |  |  | Y
N |  | Identifier for third-party items to through out from 2.1 | Buyer |  |  |  |  | Investigate which Sales units have extended third party items to their local assortment & stop 2.1 for these |  |  |  |  | Y
N |  | Persona to be mastered in C4C instead of in C3 | Buyer | [9 empty] | Y
N |  | Add Persona to C4C API to Servicemax and SPQ+ | Buyer | [9 empty] | Y
| DMND0036447 | If non-remanufacturable options from SKF4ME in SVMX - make new information on SVMX RMA parts order lines available | Service |  |  |  | Michaela Forster to align/ prioritize this with Anders Larsson
| DMND0036446 | Requested delivery date from SKF4ME to ServiceMax RMA parts order line - create new field in SVMX | Service |  |  |  | Michaela Forster to align/ prioritize this with Anders Larsson
| DMND0036190 | "Certificate" allow to receive this information from SKF4ME and show on WO in SVMX | Service |  |  |  | Michaela Forster to align/ prioritize this with Anders Larsson
| DMND0036448 | Automize child works order creation with step of RMA receive | Service |  |  |  | Michaela Forster to align/ prioritize this with Anders Larsson | Out of scope for Reman version 1
| DMND0036449 | MBC Transp Mark Text from SKF4Me to SVMX -> add fields in SVMX and to display them on the delivery paper | Service |  |  |  | Michaela Forster to align/ prioritize this with Anders Larsson
| DMND0036602 | Automate the creation of RMA output document in Servicemax | Service |  |  |  | Michaela Forster to align/ prioritize this with Anders Larsson
| DMND0037074 | Add one more field for scheduled date with the purpose to ensure the digital service can read previous scheduled date & new scheduled date in a scenario when the scheduled date was changed. Add one more field also to store update of qty and price. | Service |  |  |  | Hanna Sandberg to align with Michaela Forster/ get DMND no
| DMND0036475 | The customer can from item level order book send request (ticket) for CX to manually edit/ cancel |  |  |  |  | SFM Front End | With this demand the customer can from item level in SFM order book send request (ticket) for CX to manually edit/ cancel if the order line if it is in status Pending or Booked. CX to manually investigate the possibilities to accommodate & respond to the customer via email. In a scenario when the order line has another status than Pending or Booked, the following message is to be displayed "Request for change not allowed". The customer will have a few more pre-defined options to request updates of order header data, for example to change the delivery address etc. Also, the feedback was given for this demand to be developed in alignment with DMND0034282 Item(s) on this line cannot be returned, cancelled, refunded, postponed, or decreased in quantity. What we get with DMND0034282 is Pack variant Classification Code(PCC) in P&A, Order Fetch and Scheduling Agreement Fetch APIs and use PCC in SFM to display relevant warning messages to customers if a product cannot be decreased in quantity, postponed, cancelled, returned, or refunded. In summary: in a scenario when SFM receive PCC N or Q it will display the message Item(s) on this line cannot be returned, cancelled... & will accordingly limit the possibilities for the customer to request order updates to e.g. delivery address etc., changes to quantity & requested date will not be allowed. Please note SFM has a JIRA ticket S4M 7272 for this already that can be refined based on the presentation attached in Servicenow on this demand.
| DMND0034437 | SFM to prevent that the customer unintentionally sends in quote request for qty 1 when they want higher quantity Highlight the rows that were updated since the last time the customer logged in. After the customer has clicked on status update on order line/ quote, status update on C4C ticket/ SVMX ticket (not yest in SFM production) Mass change requeste date. SFM to put requested date as todays date |  |  |  |  | SFM Front End
| DMND0032866 | SFM - Improve Convert Order process - remove Accept Quote step
| DMND0032312 | Matrix discount in PnA check. Universal requirement for EMEA. C3 setting required/ only relevant for Distributors.
| IDEA0031970, | SFM Dashboard setup Report
DMND0032698
| DMND0019814/5 | Low value inquiries logic in SFM
| DMND0031243, | List credit note data and download PDF
PRJ020421526
| IDEA0030680 | Edit /cancel sales orders
| IDEA0029083 | Lines with ZTAS items in SFM order book
| IDEA0031024/ | Create setting in C3 on Sales Unit respectively on Sold-to level
DMND0031825
| IDEA0030681 | Order Fetch API includes delivery priority, display it in SFM
| IDEA0031379 | SFM Orderbook includes Booked (BOK/ ALL), Packed (RPI)